## Executive Summary
Ralph Analytics — AI Laws & Regulations Compliance Analysis
Ralph Analytics AI Compliance Analysis — Updated 26 June 2026 ¦ v2.0
SYSTEM CONTEXT: Ralph Analytics is a B2B SaaS platform for M&E analytics, regulatory compliance management, ESG/supply chain monitoring, and AI-assisted audit analysis. AI components (ralph-ai via OpenAI GPT-4o) analyse documents, generate gap analysis, and produce narrative summaries. Ralph does NOT make automated employment, credit, or legal decisions about natural persons. Ralph is classified as an AI DEPLOYER — not a provider or developer of AI models.
LIMITED RISK | 2 GAPS | ALIGNED | MONITOR | 5 GAPS | 10 GAPS | COMPLIANT | 74%
Not High-Risk | Major gaps closed | Policy Met | Low Exposure | Action Needed | Action Needed | Sector-Led | Good Progress
Not High-Risk | Urgent | Policy Met | Low Exposure | Action Needed | Action Needed | Sector-Led | Needs Work
EU AI Act (Reg. 2024/1689) | European Union | Yes — Aug 2026 | Limited Risk (Art.50) | Partial | 2 | AI disclosure added ✅ ¦ DPIA signed ✅ ¦ High-Risk review by 1 Aug 2026
POPIA (Act 4 of 2013) | South Africa | Yes — Enforceable NOW | Medium | Partial | 2 | IO registered ✅ ¦ Privacy Policy live ✅ ¦ PAIA Manual live ✅ ¦ OpenAI DPA signed ✅ ¦ Consent forms Q3 2026
SA National AI Policy | South Africa | No (policy guidance) | Low | Aligned | 1 | Monitor Cabinet approval. RA-POL-AI-001 aligned ✅
GDPR (Reg. 2016/679) | EU / EEA | Yes (if EU clients) | Low — monitor | Partial | 3 | OpenAI DPA + SCCs ✅ ¦ Privacy Policy updated ✅ ¦ DPIA complete ✅ ¦ Legal basis register Q3 2026
UK AI Framework | United Kingdom | Sector-led, voluntary | Low | Compliant | 0 | No UK clients currently. ICO/FCA mapping on UK onboarding.
NIST AI RMF 1.0 | United States | Voluntary | Low | Partial | 4 | GOVERN ✅ ¦ MAP ✅ ¦ MEASURE: bias testing Q3 2026 ¦ MANAGE: register Q3 2026
ISO/IEC 42001:2023 | International | Voluntary (certifiable) | Medium | In Progress | 7 | Gap assessment Q3 2026 → AIMS docs Q4 2026 → Internal audit Q1 2027 → Cert Q2 2027
African Union AI Strategy | Africa | Policy | Low | Aligned | 0 | Data sovereignty statement in Privacy Policy ✅
ISO/IEC 42001:2023 | International | Voluntary (certifiable) | Medium | Partial | 10 | AI Policy · Risk Assessment · Impact Assessment · Governance role
African Union AI Strategy 2024 | Africa | Policy | Low | Aligned | 1 | Add data sovereignty statement for African clients
Last updated: 26 June 2026 ¦ v2.0 ¦ NEXT CRITICAL DATE: 2 August 2026 — EU AI Act full applicability

## EU AI Act
EU AI Act (Regulation 2024/1689) — Detailed Compliance Analysis
Ralph Analytics AI Compliance Analysis — 26 June 2026
The EU AI Act is the world's first comprehensive AI law. Prohibited AI provisions applied from Feb 2025. High-risk AI (Annex III) obligations apply from Aug 2026. RALPH'S ROLE: Deployer (not provider) of a 3rd-party GPAI model (OpenAI GPT-4o). Ralph's AI is used for document analysis and report generation — assessed below.
|  |  | Compliant ✅ | None | None required | N/A
Article / Requirement | Applies to Ralph? | Current Position | Monitor | Annual Annex III self-assessment required. High-Risk reclassification risk if client use scope expands. | Document intended use; prohibit high-risk use in T&Cs; annual Annex III self-assessment before Aug 2026. | Before Aug 2026
Art. 5 — Prohibited AI systems (social scoring, biometric ID, manipulation) | No — Ralph does none of the prohibited categories | AI limited to document/compliance analysis. No social scoring, emotion inference, or biometric identification. | Done ✅ | Closed — AI disclosure paragraph in all deliverables. Portal transparency banner active. | Complete ✅ — AI disclosure on all outputs. RA-POL-AI-001 v1.1 documents requirement. | Done
Art. 6 + Annex III — High-Risk AI classification (employment §4, law enforcement §8, education §3) | Borderline — monitor as use cases evolve | Ralph analyses supplier compliance docs, not individuals. Not currently high-risk. RISK: if clients use AI outputs for employment/HR decisions. | Partial | Human oversight policy in RA-POL-AI-001 ✅. 'Flag for human review' UI button not yet built in portal. | Add 'Flag for human review' button in client portal. Sprint 5. | Sprint 5
Art. 13 — Transparency (users must know they interact with AI) | Yes — all AI-generated analysis must be identifiable | No AI disclosure exists anywhere on the platform or in exports | Partial | AI output logging via AI Governance dashboard ✅. OpenAI deployer docs reviewed ✅. Performance metrics Q3 2026. | AI Governance dashboard active ✅. Performance metrics (accuracy, hallucination rate) Q3 2026. | Ongoing
Art. 14 — Human oversight (deployers must enable human review) | Yes — Ralph as deployer must ensure human oversight is possible | No 'flag for review' or override mechanism. No documented review process. | Done ✅ | Closed — AI disclosure added to all AI-assisted client deliverables. Transparency banner in portal. | Complete ✅ — AI disclosure statement + portal banner. | Done
Art. 25 — Deployer obligations (instructions of use, logging, monitoring) | Yes — applies to all AI deployers | No AI output logs. No review of OpenAI's instructions of use. No monitoring of AI performance. | Compliant ✅ | None — Ralph is a deployer. OpenAI confirmed EU AI Act Code of Practice adherence Aug 2025. | Monitor OpenAI compliance annually. | Ongoing
Art. 50 — Transparency for AI-generated content | Yes — AI-generated reports sent to clients | No disclosure in client-facing reports that content is AI-generated | Monitor | Not yet high-risk. DPIA RA-DPIA-AI-001 completed as precautionary measure ✅. | DPIA signed ✅. Review if use case scope expands to Annex III. | Ongoing
Art. 53 — GPAI provider obligations | No — OpenAI is the GPAI provider, not Ralph | Ralph is a downstream deployer only. OpenAI carries provider obligations. | Done ✅ | Closed — AI usage clause in PSA Clause 7. Disclosure in client onboarding materials. | Complete ✅ — PSA Clause 7 + Privacy Policy updated. | Done
Art. 9 — Risk management system (high-risk AI only) | Not yet — only if Annex III classification applies | No AI risk management system in place | Monitor | Required if reclassified as high-risk | Build AI risk register as part of ISO 42001 implementation (dual value) | Before Aug 2026
Recital 12 + Art. 28 — B2B AI output disclosure | Yes — Ralph delivers AI outputs to enterprise clients | No disclosure in client contracts or deliverables that AI is used | Gap | Contractual and regulatory non-disclosure risk | Add AI usage clause to client agreements; disclose in onboarding | Immediately

## POPIA & SA Laws
POPIA + South Africa AI Policy — Compliance Analysis
Ralph Analytics AI Compliance Analysis — 26 June 2026
POPIA (Protection of Personal Information Act 4 of 2013) is fully enforceable with fines up to R10 million. Ralph Analytics is incorporated and operated in South Africa and processes personal data of users and potentially data subjects in client compliance records. PRIORITY: POPIA gaps are the most immediate legal risk — enforcement is active.
|  | Done ✅ | IO designated and registered with Information Regulator ✅. Contact published at admin@ralph-analytics.com. | Closed | Complete ✅ | Done
Requirement | POPIA Section | Done ✅ | PAIA Manual live at ralph-analytics.com/paia ✅. | Closed | Complete ✅. Annual review due June 2027. | Done
Information Officer registration with Information Regulator | S1 + S55 | Done ✅ | Privacy Policy live at ralph-analytics.com/privacy ✅. Full AI transparency section (6 sub-sections) added June 2026. | Closed | Complete ✅. AI transparency section updated June 2026. | Done
PAIA Manual — mandatory for all SA private bodies | PAIA S51 | Partial | Lawful basis documented in RA-POL-AI-001 for AI. Formal legal basis register not yet created. | Legal basis register missing | Create formal legal basis register per processing activity. | Q3 2026
Privacy Policy / Information Notice | S18 | Partial | DSR contact email exists ✅. Formal documented 30-day response procedure not yet formalised. | Formal DSR procedure pending | Document DSR procedure and 30-day response SLA. Q3 2026. | Q3 2026
Lawful basis for processing personal data | S11 | Partial | Passwords bcrypt-hashed ✅. MySQL/MariaDB with env credentials ✅. Formal security policy document pending. | Security policy document pending | Draft and publish formal security policy. Q3 2026. | Q3 2026
Data subject rights — access, correction, deletion, objection | S23–25 | Done ✅ | OpenAI Enterprise DPA signed ✅. SanitiseForAI strips PII from all prompts ✅. Policy in RA-POL-AI-001. | Closed | Complete ✅ — DPA signed. PII stripping deployed. Policy documented. | Done
Security safeguards for personal information | S19 | Done ✅ | OpenAI DPA includes EU SCCs ✅. Transfer Impact Assessment documented ✅. Basis documented in Privacy Policy. | Closed | Complete ✅ — SCCs in place. TIA on file. Privacy Policy updated. | Done
Operator agreements with third-party processors (OpenAI) | S20–21 | Done ✅ | RA-POL-AI-001 requires mandatory human review of all AI outputs ✅. No automated decisions affecting individuals. | Closed | Complete ✅ — Human oversight policy active. | Done
Cross-border data transfer (personal data → US via OpenAI) | S72 | Partial | AI transparency in Privacy Policy updated June 2026 ✅. Consent forms for POPIA April 2025 amendments: Q3 2026. | Updated consent forms for April 2025 amendments pending | Update client consent forms per POPIA April 2025 Regulation amendments. Q3 2026. | Q3 2026
Automated decision-making affecting individuals | S71 | Monitor | AI generates compliance/risk scores affecting supplier relationships | If scores affect individuals' rights, human review required before decisions | Document that all AI outputs require human review before action | 60 days
SA AI Policy — Transparency obligation | Policy Pillar 1 | Partial | No AI disclosure anywhere on platform or in reports | Policy alignment gap; sets precedent for future legislation | Add AI transparency notice to platform and all exported reports | 30 days
SA AI Policy — Bias monitoring and fairness | Policy Pillar 4 | Gap | No bias monitoring or fairness testing of AI-generated compliance scores | Risk of discriminatory outputs; future legislative risk | Implement periodic bias audits; document AI fairness testing process | 90 days
Cybercrimes Act — security of AI systems and data | Cybercrimes Act 19 of 2020 | Partial | SSH access only; no WAF; no intrusion detection; no formal incident response plan | Inadequate protection against unauthorised access to AI system | Implement WAF (Cloudflare); document incident response plan; enable server monitoring | 60 days

## ISO 42001 & NIST RMF
ISO/IEC 42001:2023 + NIST AI RMF 1.0 — Gap Analysis
Ralph Analytics AI Compliance Analysis — 26 June 2026
ISO/IEC 42001:2023 is the first international AI Management System standard. NIST AI RMF 1.0 is the US framework for AI risk management. Both are voluntary but increasingly expected by enterprise clients and regulators. Implementing these frameworks will simultaneously address EU AI Act Art. 9 and SA AI Policy requirements.
|  |  | RA-POL-AI-001 v1.1 in place ✅. Defines principles, uses, prohibited uses, roles, objectives. | Done ✅ | Closed | Complete ✅ — AI Governance Policy v1.1 active.
Requirement | Framework | Clause / Core Function | No measurable AI objectives defined (accuracy rate, hallucination rate, human review %). | Gap | No measurable objectives baseline | Define 3–5 measurable AI objectives. Q3 2026.
AI Policy — documented organisational AI policy and principles | ISO 42001 | Cl. 5.2 | EU AI Act risk classification in RA-POL-AI-001 ✅. ISO 42001-structured risk assessment pending. | Partial | ISO risk assessment pending | Conduct ISO 42001-format AI risk assessment. Q3 2026.
AI Objectives — measurable AI performance targets | ISO 42001 | Cl. 6.2 | DPIA RA-DPIA-AI-001 signed ✅. ISO 42001-format AI impact assessment not yet conducted. | Partial | ISO impact assessment pending | Conduct ISO 42001-format AI impact assessment. Q3 2026.
AI Risk Assessment — structured risk identification process | ISO 42001 | Cl. 6.1 | MD oversight ✅. IO registered ✅. Data/AI Lead defined in RA-POL-AI-001 ✅. | Done ✅ | Closed | Complete ✅ — Governance roles in place.
AI Impact Assessment — assess impact on people and society | ISO 42001 | Cl. 8.4 | AI Governance dashboard active ✅. AI interactions logged ✅. Performance metrics pending. | Partial | Performance metrics not tracked | Implement AI performance metrics. Q3 2026.
Roles & Responsibilities — designated AI governance role | ISO 42001 | Cl. 5.3 | RA-POL-AI-001 lists prohibited uses ✅. Approved use cases ✅. New use case approval process ✅. | Done ✅ | Closed | Complete ✅ — Permitted and prohibited uses documented.
Data Quality — input data governance for AI systems | ISO 42001 | Cl. 8.3 | Mandatory human review in RA-POL-AI-001 ✅. AI logs active ✅. Formal Human Oversight SOP pending. | Partial | SOP document pending | Draft standalone Human Oversight SOP. Q3 2026.
Human Oversight — documented review process for AI outputs | ISO 42001 | Cl. 8.6 | GOVERN ✅ ¦ MAP (risk classification) ✅ ¦ MEASURE: bias testing pending ¦ MANAGE: policy ✅, register pending | Partial | MEASURE function pending | Implement bias testing and accuracy benchmarking. Q3 2026.
AI Incident Management — log and respond to AI failures | ISO 42001 | Cl. 10.1 | Incident management in RA-POL-AI-001 ✅. Formal AI incident register and runbook pending. | Partial | AI incident register pending | Create AI incident register and runbook. Q3 2026.
Supplier AI Obligations — manage AI subprocessors | ISO 42001 | Cl. 8.7 | No AIMS internal audit schedule. No management review process. | Gap | AIMS audit process not in place | Schedule quarterly AI management reviews. Internal AIMS audit Q1 2027.
Continual Improvement — monitor AI system performance | ISO 42001 | Cl. 10.2 | No corrective action register for AI nonconformities. | Gap | Corrective action register missing | Create AIMS corrective action register. Q3 2026.
GOVERN — Establish AI risk governance structure | NIST AI RMF | GOVERN 1.0 / 1.2 | No AIMS documentation suite beyond RA-POL-AI-001 and DPIA. | Gap | AIMS documentation suite pending | Build AIMS docs: SoA, risk register, training records, deployment records. Q4 2026.
MAP — Categorise AI risks and identify context | NIST AI RMF | MAP 1.0 / 2.0 | No staff AI governance training records maintained. | Gap | Training records not maintained | Mandatory AI governance training with tracked completion records. Q3 2026.
MEASURE — Test and evaluate AI performance and bias | NIST AI RMF | MEASURE 2.0 / 2.5 | Not started. Target: Stage 1 gap assessment Q3 2026 → certification Q2 2027. | Not Started | Certification pathway not initiated | Stage 1 gap assessment Q3 2026. Certification body engagement Q1 2027.
MANAGE — Treat and mitigate identified AI risks | NIST AI RMF | MANAGE 1.0 / 2.0 | No risk treatment plans for identified AI risks | Gap | All identified risks persist with no mitigation | Create risk treatment register; assign owners; track to closure
MANAGE — Incident response for AI failures | NIST AI RMF | MANAGE 3.0 | No AI-specific incident response plan | Gap | Systematic failures in AI outputs cannot be detected or resolved | Draft AI incident response procedure with severity levels and communication protocol

## Compliance Action Plan
Ralph Analytics — AI Compliance Action Plan (Prioritised)
Ralph Analytics AI Compliance Analysis — 26 June 2026
# | Action | Regulations Addressed | Priority | Effort | Deadline | Owner | Notes | Status
1 | Add 'AI-assisted analysis' disclosure to all AI-generated outputs in client portal | EU AI Act Art.13/50 · SA AI Policy | Critical | Low | This week | Dev | AI disclosure paragraph added to all deliverables. Portal transparency banner live. June 2026. | Done ✅
2 | Add AI usage clause to all client contracts and onboarding materials | EU AI Act Art.28 · Recital 12 | Critical | Low | This week | Management | PSA Clause 7 AI services clause in all contracts. Onboarding materials updated. June 2026. | Done ✅
3 | Designate & register Information Officer with SA Information Regulator | POPIA S55 | Critical | Low | 30 days | Director/Management | IO registered with Information Regulator ✅. Contact: admin@ralph-analytics.com. | Done ✅
4 | Draft and publish Privacy Policy on ralph-analytics.com | POPIA S18 · GDPR · EU AI Act | Critical | Medium | 30 days | Legal/Dev | PAIA Manual published at ralph-analytics.com/paia ✅. | Done ✅
5 | Draft and publish PAIA Manual | PAIA S51 | Critical | Medium | 30 days | Legal | Privacy Policy live at ralph-analytics.com/privacy ✅. Full AI section added June 2026. | Done ✅
6 | Document lawful basis for each data processing activity | POPIA S11 | Critical | Low | 30 days | Legal | OpenAI Enterprise DPA signed ✅. SCCs in place. TIA documented. June 2026. | Done ✅
7 | Establish Data Processing Agreement (DPA) with OpenAI | POPIA S21 · GDPR Art.28 | Critical | Low | 30 days | Management | RA-POL-AI-001 v1.1 published ✅. Permitted and prohibited AI uses documented. | Done ✅
8 | Implement prompt hygiene — strip PII from all AI prompts | POPIA S72 · GDPR Art.44 | Critical | Medium | 30 days | Dev | DPIA RA-DPIA-AI-001 signed ✅ (GDPR Art.35 / POPIA S22). Approved to proceed. | Done ✅
9 | Create Data Subject Rights process (access, deletion, correction) | POPIA S23–25 · GDPR Art.15–17 | High | Medium | 60 days | Legal/Dev | SanitiseForAI utility deployed ✅. PII stripped from all AI prompts. | Done ✅
10 | Draft AI Policy document — principles, scope, prohibited uses, roles | ISO 42001 Cl.5.2 · NIST GOVERN | High | Medium | 60 days | Management | AI Governance dashboard active ✅. All AI interactions logged with timestamp. | Done ✅
11 | Conduct AI Risk Assessment (hallucination, bias, misuse, accuracy) | ISO 42001 Cl.6.1 · NIST MAP | High | Medium | 60 days | Management/Dev | GOVERN ✅ ¦ MAP ✅ ¦ MEASURE: bias testing Q3 2026 ¦ MANAGE: incident register Q3 2026. | In Progress
12 | Conduct AI Impact Assessment for ralph-ai compliance scoring | ISO 42001 Cl.8.4 · EU AI Act Art.9 | High | Medium | 60 days | Management | Formal legal basis register not yet created. GDPR Art.30 / POPIA requirement. | Q3 2026
13 | Assign AI Responsible Officer — define duties and accountability | ISO 42001 Cl.5.3 · NIST GOVERN 1.2 | High | Low | 30 days | Management | DSR email exists ✅. Formal 30-day response procedure document pending. | Q3 2026
14 | Implement 'Flag for human review' on AI-generated analysis | EU AI Act Art.14 · ISO 42001 Cl.8.6 | High | Medium | Sprint 5 | Dev | MySQL/MariaDB in place ✅. Formal security policy document pending. | Q3 2026
15 | Implement AI output logging (timestamp, model, prompt hash, user) | EU AI Act Art.25 · ISO 42001 Cl.8.5 | High | Medium | Sprint 5 | Dev | SA-specific AI bias assessment for GPT-4o. SA AI Policy alignment. | Q3 2026
16 | Document cross-border data transfer basis for OpenAI (US) | POPIA S72 · GDPR Art.44–49 | Medium | Low | 60 days | Legal | Formal AI incident register and runbook. Link to IO breach notification process. | Q3 2026
17 | Create AI Incident Register — log hallucinations, bias, failures | ISO 42001 Cl.10.1 · NIST MANAGE 3.0 | Medium | Medium | 90 days | Dev | 72-hour breach notification procedure and templates (POPIA S22 / GDPR Art.33). | Q3 2026
18 | Implement prompt template library — validated prompts for all AI calls | ISO 42001 Cl.8.3 · NIST MEASURE | Medium | Medium | Sprint 5/6 | Dev | Client consent forms for POPIA April 2025 amendments (new objection/correction procedures). | Q3 2026
19 | Document AI human oversight SOP — who reviews, when, and how | ISO 42001 Cl.8.6 · NIST MANAGE 1.0 | Medium | Low | 60 days | Management | OpenAI sub-processor monitoring. Audit all other AI tool vendors for DPA compliance. | Q3 2026
20 | Review OpenAI's EU AI Act + ISO 42001 compliance documentation | ISO 42001 Cl.8.7 | Medium | Low | 30 days | Management | AIMS documentation suite: SoA, risk register, training records, deployment records. | Q4 2026
21 | Implement monthly AI output quality and bias review | ISO 42001 Cl.10.2 · NIST MEASURE 2.0 | Medium | Medium | 90 days | Dev/Mgmt | Measurable AI objectives: GPT-4o accuracy rate, hallucination rate, human review %. | Q4 2026
22 | Implement database encryption at rest (migrate JSON → MySQL) | POPIA S19 · ISO 42001 | Medium | High | Sprint 5 | Dev | Internal AIMS audit. Quarterly AI management reviews begin Q3 2026. | Q1 2027
23 | Implement WAF and server intrusion detection | Cybercrimes Act · POPIA S19 | Medium | Medium | 60 days | Dev | ISO 42001 certification body engagement. Stage 1 gap assessment Q3 2026. | Q2 2027
24 | Monitor EU Annex III as Ralph's use cases evolve | EU AI Act Art.6/Annex III | Low | Low | Ongoing | Management | Annual self-assessment — document findings | Ongoing
25 | Map to UK ICO AI guidance when onboarding UK clients | UK AI Framework | Low | Low | Before UK clients | Management | ICO guidance on AI and data protection applies | Pending
COMPLETED: 10/23 (43%) | REMAINING: 13 actions ¦ Next critical date: 2 August 2026 — EU AI Act full applicability | Last updated: 26 June 2026